## Pivot_Analysis
Row Labels | Average of Planned % | Average of Actual %
Civil | 96.25 | 81.25
Coating | 40 | 0
Document Control | 0 | 0
Electrical | 15 | 0
Instrumentation | 20 | 10
Mechanical | 56 | 39
QA/QC | 50 | 41.25
Structural | 75 | 60
Grand Total | 52.5 | 38.25

## Pivot_Status
Row Labels | Count of Activity_ID
Completed | 2
Delayed | 3
In Progress | 7
Not Started | 8
Grand Total | 20

## qry_ProjectProgress_Clean
Activity_ID | Activity | Discipline | Responsible_Team | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned % | Actual % | Status | Delay_Days | Progress_Variance | Performance_Status | Schedule_Status
A001 | Foundation Excavation | Civil | Civil Team | 2026-08-01 | 2026-08-05 | 2026-08-01 | 2026-08-05 | 100 | 100 | Completed | 0 | 0 | On Track | On Schedule
A002 | Foundation Concrete | Civil | Civil Team | 2026-08-04 | 2026-08-10 | 2026-08-05 | 2026-08-11 | 100 | 90 | Delayed | 1 | -10 | Slightly Behind | Delayed
A003 | Structural Steel Installation | Structural | Steel Team | 2026-08-08 | 2026-08-18 | 2026-08-09 |  | 75 | 60 | In Progress |  | -15 | Significantly Behind | Not Completed
A004 | Equipment Installation | Mechanical | Mechanical Team | 2026-08-10 | 2026-08-20 | 2026-08-12 |  | 60 | 40 | In Progress |  | -20 | Significantly Behind | Not Completed
A005 | Piping Installation | Mechanical | Piping Team | 2026-08-12 | 2026-08-25 | 2026-08-13 |  | 45 | 30 | In Progress |  | -15 | Significantly Behind | Not Completed
A006 | Cable Tray Installation | Electrical | Electrical Team | 2026-08-15 | 2026-08-25 |  |  | 20 | 0 | Not Started |  | -20 | Significantly Behind | Not Completed
A007 | Electrical Cable Pulling | Electrical | Electrical Team | 2026-08-18 | 2026-08-30 |  |  | 10 | 0 | Not Started |  | -10 | Slightly Behind | Not Completed
A008 | HVAC Installation | Mechanical | HVAC Team | 2026-08-05 | 2026-08-15 | 2026-08-06 |  | 80 | 70 | In Progress |  | -10 | Slightly Behind | Not Completed
A009 | Fire Protection Piping | Mechanical | Fire Team | 2026-08-07 | 2026-08-17 | 2026-08-08 |  | 70 | 55 | In Progress |  | -15 | Significantly Behind | Not Completed
A010 | Equipment Testing | QA/QC | QA Team | 2026-08-20 | 2026-08-25 |  |  | 0 | 0 | Not Started |  | 0 | On Track | Not Completed
A011 | Welding Inspection | QA/QC | QA Team | 2026-08-09 | 2026-08-12 | 2026-08-10 | 2026-08-13 | 100 | 100 | Completed | 1 | 0 | On Track | Delayed
A012 | Material Inspection | QA/QC | QA Team | 2026-08-11 | 2026-08-14 | 2026-08-11 |  | 80 | 65 | In Progress |  | -15 | Significantly Behind | Not Completed
A013 | Painting Works | Coating | Painting Team | 2026-08-14 | 2026-08-22 |  |  | 40 | 0 | Not Started |  | -40 | Significantly Behind | Not Completed
A014 | Insulation Works | Mechanical | Insulation Team | 2026-08-16 | 2026-08-28 |  |  | 25 | 0 | Not Started |  | -25 | Significantly Behind | Not Completed
A015 | Structural Inspection | QA/QC | QA Team | 2026-08-17 | 2026-08-20 |  |  | 20 | 0 | Not Started |  | -20 | Significantly Behind | Not Completed
A016 | Road Preparation | Civil | Civil Team | 2026-08-02 | 2026-08-12 | 2026-08-03 |  | 100 | 75 | Delayed |  | -25 | Significantly Behind | Not Completed
A017 | Drainage Installation | Civil | Civil Team | 2026-08-06 | 2026-08-16 | 2026-08-07 |  | 85 | 60 | Delayed |  | -25 | Significantly Behind | Not Completed
A018 | Instrument Installation | Instrumentation | Instrument Team | 2026-08-13 | 2026-08-24 | 2026-08-14 |  | 35 | 20 | In Progress |  | -15 | Significantly Behind | Not Completed
A019 | Instrument Testing | Instrumentation | Instrument Team | 2026-08-22 | 2026-08-30 |  |  | 5 | 0 | Not Started |  | -5 | Slightly Behind | Not Completed
A020 | Final Documentation | Document Control | Document Team | 2026-08-25 | 2026-08-31 |  |  | 0 | 0 | Not Started |  | 0 | On Track | Not Completed

## Dashboard
Project Progress KPI Dashboard
Total Activities | Completed Activities | In Progress | Completed Late | Avg. Actual Progress | Avg. Progress Variance
20 | 2 | 7 | 2 | 38.25 | -14.25

## Raw_Data
Activity_ID | Activity | Discipline | Responsible_Team | Planned Start | Planned Finish | Actual Start | Actual Finish | Planned % | Actual % | Status
A001 | Foundation Excavation | Civil | Civil Team | 2026-08-01 | 2026-08-05 | 2026-08-01 | 2026-08-05 | 100 | 100 | Completed
A002 | Foundation Concrete | Civil | Civil Team | 2026-08-04 | 2026-08-10 | 2026-08-05 | 2026-08-11 | 100 | 90 | Delayed
A003 | Structural Steel Installation | Structural | Steel Team | 2026-08-08 | 2026-08-18 | 2026-08-09 |  | 75 | 60 | In Progress
A004 | Equipment Installation | Mechanical | Mechanical Team | 2026-08-10 | 2026-08-20 | 2026-08-12 |  | 60 | 40 | In Progress
A005 | Piping Installation | Mechanical | Piping Team | 2026-08-12 | 2026-08-25 | 2026-08-13 |  | 45 | 30 | In Progress
A006 | Cable Tray Installation | Electrical | Electrical Team | 2026-08-15 | 2026-08-25 |  |  | 20 | 0 | Not Started
A007 | Electrical Cable Pulling | Electrical | Electrical Team | 2026-08-18 | 2026-08-30 |  |  | 10 | 0 | Not Started
A008 | HVAC Installation | Mechanical | HVAC Team | 2026-08-05 | 2026-08-15 | 2026-08-06 |  | 80 | 70 | In Progress
A009 | Fire Protection Piping | Mechanical | Fire Team | 2026-08-07 | 2026-08-17 | 2026-08-08 |  | 70 | 55 | In Progress
A010 | Equipment Testing | QA/QC | QA Team | 2026-08-20 | 2026-08-25 |  |  | 0 | 0 | Not Started
A011 | Welding Inspection | QA/QC | QA Team | 2026-08-09 | 2026-08-12 | 2026-08-10 | 2026-08-13 | 100 | 100 | Completed
A012 | Material Inspection | QA/QC | QA Team | 2026-08-11 | 2026-08-14 | 2026-08-11 |  | 80 | 65 | In Progress
A013 | Painting Works | Coating | Painting Team | 2026-08-14 | 2026-08-22 |  |  | 40 | 0 | Not Started
A014 | Insulation Works | Mechanical | Insulation Team | 2026-08-16 | 2026-08-28 |  |  | 25 | 0 | Not Started
A015 | Structural Inspection | QA/QC | QA Team | 2026-08-17 | 2026-08-20 |  |  | 20 | 0 | Not Started
A016 | Road Preparation | Civil | Civil Team | 2026-08-02 | 2026-08-12 | 2026-08-03 |  | 100 | 75 | Delayed
A017 | Drainage Installation | Civil | Civil Team | 2026-08-06 | 2026-08-16 | 2026-08-07 |  | 85 | 60 | Delayed
A018 | Instrument Installation | Instrumentation | Instrument Team | 2026-08-13 | 2026-08-24 | 2026-08-14 |  | 35 | 20 | In Progress
A019 | Instrument Testing | Instrumentation | Instrument Team | 2026-08-22 | 2026-08-30 |  |  | 5 | 0 | Not Started
A020 | Final Documentation | Document Control | Document Team | 2026-08-25 | 2026-08-31 |  |  | 0 | 0 | Not Started

## Project_Summary
Project Progress KPI Dashboard — Project Summary
Business Problem | Project teams need a clear view of progress, schedule performance, and activities requiring attention.
Objective | Build an Excel dashboard that compares planned versus actual progress and highlights project status and delays.
Data Source | Project activity tracker with 20 activities, disciplines, dates, planned/actual progress, and status.
Tools Used | Excel, Power Query, PivotTables, PivotCharts, and formulas.
Key Finding | Actual progress is 38.25% versus 52.5% planned progress: a 14.25 percentage-point shortfall.
Business Impact | Helps managers identify delayed work, monitor progress by discipline, and focus recovery actions on problem areas.